## Project Data
Project Name | Backup Cluster Manager SEP
Online team meeting | https://tu-berlin.zoom-x.de/j/66460442542?pwd=6JDdHFzvrTj3bJokdNJSYxHA3b8F6r.1
Production system (if any) | TBD
Test system (if any) | TBD
GitHub repository | https://github.com/amosproj/amos2025ws02-backup-cluster-manager
GitHub feature board | https://github.com/orgs/amosproj/projects/90
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/94
Team T-shirt (white) | ...
Team T-shirt (black) | ...
Additional materials | Discord: https://discord.gg/mhFBrsTx
Team maling list | oss-amos-proj2@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Wysokinska | Xemena | xenia1w | xenia.wysokinska@gmail.com
Ostrizki | Jan | Stringrimm
Raju | Robin Jose | robinrj6 | robin.jose.raju@fau.de
Nogu | Ervin | ervinn09
Krüger | Landolf | krueger-hash | l.krueger.1@campus.tu-berlin.de
Tröger | Nicolas | fe27hity
Treijner | Arda | ArdaMT
Killer | Hans | HansKiller-TH | hans.killer@fau.de
Schulze | Levin | p0d3x

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
0 | 2025-10-15 | - | - | Everyone else | - | Xemena Wysokinska | First Meeting
1 | 2025-10-22 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
2 | 2025-10-29 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska
3 | 2025-11-05 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska | Build Process Review
4 | 2025-11-12 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska
5 | 2025-11-19 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
6 | 2025-11-26 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska | Mid-term due
7 | 2025-12-03 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
8 | 2025-12-10 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska
9 | 2025-12-17 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
10 | 2026-01-07 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska
11 | 2026-01-14 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
12 | 2026-01-21 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska
13 | 2026-01-28 | Levin Schulze | Jan Ostrizki | Everyone else |  | Xemena Wysokinska
14 | 2026-02-04 | Jan Ostrizki | Levin Schulze | Everyone else |  | Xemena Wysokinska | Demo day!
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals
Fulfill the needs of our customer (SEP) Working Prototype Good team experience Learn more/Gaining experience about working agile Sharing knowledge among each other Transparent culture & good communication Learn how to open-source
Meeting norms
Weeklies: At 12:30 on Wednesday on Zoom (https://tu-berlin.zoom-x.de/j/66460442542?pwd=6JDdHFzvrTj3bJokdNJSYxHA3b8F6r.1) 90 mins. Weekly/Bi-Weekly Sync with SEP On time, give notice if someone can’t make/with delay Raising hands for better communication flow in bigger meetings like e.g. weekly
Working norms
Developers have a cutoff day a before at noon Revert if MR if it breaks other code and if there is no time for a fix Use a CI build/test pipeline MR with random reviewer (preferably a nominated one)
Coordination norms
Coordination over Discord (https://discord.gg/mhFBrsTx) Inform others if you can’t work temporarily
Communication norms
Communication over mainly on Discord, Email as emergency/backup option Weekly meeting over Zoom Use webcams as possible Special channels for different groups and topics
Consideration norms
Polite, supportive, respectful, forward, formal & constructive communication English if at least one nonnative speaker present
Cont. improvement norms
Try to help each other Actional item in retro to improve the team Adapt CI and work along it. Do not try to bypass it. Additional channel on Discord if someone needs help
Rewards
Filters on Zoom (SFW!!) Small tokens
Sanctions
Not allowed to use video filters or wear a weird hat Review one additional PR Problems require intervention worst case with professor
Signatures
Scrum Master | Xemena Wysokinska
Product owner | Levin Schulze
Product owner | Jan Ostrizki
Software developer | Robin Jose Raju
Software developer | Ervin Nogu
Software developer | Landolf Krüger
Software developer | Nicolas Tröger
Software developer | Hans Killer
Software developer

## Product Goal
Product Vision | Project Mission
The reason of existence of the envisioned product (beyond this project). | The mission of this particular project (in the context of the product vision).

## Product Glossary
Term | Definition
Cluster Manager | Supervisor instance that manages a set of SEP Sesam server nodes, handles registration of nodes, manipulation and synchronization of e.g. users, groups, and permissions or other meta data. Provides a REST interface for the Frontend and proxies requests to other nodes
SEP Sesam | SEP's Backup and Recovery software product, backups and restores are managed by a SEP Sesam Server
SEP Sesam Server Node | Instance of SEP Sesam Server which shall be part of the cluster
Cluster Mode | Configuration flag on a node, indicating the node should join a cluster. In this mode, permissions and users shall be managed by the cluster manager
Supervisor Instance | Synonymous with Cluster Manager
Node Registration | Process of adding a node to a cluster
User / Group | Authenticated principals that can be created, modified and assigned permissions.
Client | A system that should be backed up by an SEP Sesam Server (e.g. a person's laptop computer)
Frontend | The primary web UI, which runs in the browser and communicates with the CM's REST endpoints (directly, or via proxy, LB, etc TBD)
Synchronization Process | The mechanism of propagating information, such as users, groups, or permissions to downstream nodes
Proxy Functionality | The ability of issuing requests or listing data from a node via the CM's REST API

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
Wysokinska | Xemena | 5 | 5 | OK
Ostrizki | Jan | 5
Raju | Robin Jose
Nogu | Ervin
Krüger | Landolf |  | 0 | No size
Tröger | Nicolas |  | 1 | Trivial size
Treijner | Arda |  | 2 | Small size
Killer | Hans |  | 3 | Medium size
Schulze | Levin |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value