## Project Data
Project Name | Backup Cluster Manager SEP
Online team meeting | https://tu-berlin.zoom-x.de/j/66460442542?pwd=6JDdHFzvrTj3bJokdNJSYxHA3b8F6r.1
Production system (if any) | TBD
Test system (if any) | TBD
GitHub repository | https://github.com/amosproj/amos2025ws02-backup-cluster-manager
GitHub feature board | https://github.com/orgs/amosproj/projects/90
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/94
Team T-shirt (white) | https://www.shirtinator.de/s/WGBu8LkSRqOJZe-LDXqisw
Team T-shirt (black) | https://www.shirtinator.de/s/jG2py-QWSDeg3IraRTb-bQ
Additional materials
Discord | https://discord.gg/mhFBrsTx
Figma Link Website | https://www.figma.com/design/kLihICBMvBVKCodv1OlY4Y/Website-Design?m=auto&t=UItPz3hhwCtSgsc5-1
Team maling list | oss-amos-proj2@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Wysokinska | Xemena | xenia1w | xenia.wysokinska@gmail.com
Ostrizki | Jan | Stringrimm | jan.ostrizki@fau.de
Raju | Robin Jose | robinrj6 | robin.jose.raju@fau.de
Nogu | Ervin | ervinn09 | ervin.nogu@campus.tu-berlin.de
Krüger | Landolf | krueger-hash | l.krueger.1@campus.tu-berlin.de
Tröger | Nicolas | fe27hity | nico.troeger@fau.de
Killer | Hans | HansKiller-TH | hanskiller@web.de
Schulze | Levin | p0d3x

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
0 | 2025-10-15 | - | - | Everyone else | - | Xemena Wysokinska | First Meeting
1 | 2025-10-22 | Jan Ostrizki | Levin Schulze | Everyone else | - | Xemena Wysokinska
2 | 2025-10-29 | Levin Schulze | Jan Ostrizki | Everyone else | Nicolas Tröger | Xemena Wysokinska
3 | 2025-11-05 | Jan Ostrizki | Levin Schulze | Everyone else | Hans Killer | Xemena Wysokinska | Build Process Review
4 | 2025-11-12 | Levin Schulze | Jan Ostrizki | Everyone else | Robin Rose Raju | Xemena Wysokinska
5 | 2025-11-19 | Jan Ostrizki | Levin Schulze | Everyone else | Ervin Nogu | Xemena Wysokinska
6 | 2025-11-26 | Levin Schulze | Jan Ostrizki | Everyone else | Landolf Krüger | Xemena Wysokinska | Mid-term due
7 | 2025-12-03 | Jan Ostrizki | Levin Schulze | Everyone else | Nicolas Tröger | Xemena Wysokinska
8 | 2025-12-10 | Levin Schulze | Jan Ostrizki | Everyone else | Hans Killer | Xemena Wysokinska
9 | 2025-12-17 | Jan Ostrizki | Levin Schulze | Everyone else | Robin Rose Raju | Xemena Wysokinska
10 | 2026-01-07 | Jan Ostrizki | Jan Ostrizki | Everyone else | Ervin Nogu | Xemena Wysokinska
11 | 2026-01-14 | Jan Ostrizki | Levin Schulze | Everyone else | Landolf Krüger | Xemena Wysokinska
12 | 2026-01-21 | Levin Schulze | Jan Ostrizki | Everyone else | Nicolas Tröger | Xemena Wysokinska
13 | 2026-01-28 | Jan Ostrizki | Levin Schulze | Everyone else | Hans Killer | Xemena Wysokinska
14 | 2026-02-04 | Levin Schulze | Jan Ostrizki | Everyone else | Robin Rose Raju | Xemena Wysokinska | Demo day!
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals
Fulfill the needs of our customer (SEP) Working Prototype Good team experience Learn more/Gaining experience about working agile Sharing knowledge among each other Transparent culture & good communication Learn how to open-source
Meeting norms
Weeklies: At 12:30 on Wednesday on Zoom (https://tu-berlin.zoom-x.de/j/66460442542?pwd=6JDdHFzvrTj3bJokdNJSYxHA3b8F6r.1) 90 mins. Weekly/Bi-Weekly Sync with SEP On time, give notice if someone can’t make/with delay Raising hands for better communication flow in bigger meetings like e.g. weekly
Working norms | Working norms
Developers have a cutoff day a before at noon Revert if MR if it breaks other code and if there is no time for a fix Use a CI build/test pipeline MR with random reviewer (preferably a nominated one)
Coordination norms
Coordination over Discord (https://discord.gg/mhFBrsTx) Inform others if you can’t work temporarily
Communication norms
Communication over mainly on Discord, Email as emergency/backup option Weekly meeting over Zoom Use webcams as possible Special channels for different groups and topics
Consideration norms
Polite, supportive, respectful, forward, formal & constructive communication English if at least one nonnative speaker present
Cont. improvement norms
Try to help each other Actional item in retro to improve the team Adapt CI and work along it. Do not try to bypass it. Additional channel on Discord if someone needs help
Rewards
Filters on Zoom (SFW!!) Small tokens
Sanctions
Not allowed to use video filters or wear a weird hat Review one additional PR Problems require intervention worst case with professor
Signatures
Scrum Master | Xemena Wysokinska
Product owner | Levin Schulze
Product owner | Jan Ostrizki
Software developer | Robin Jose Raju
Software developer | Ervin Nogu
Software developer | Landolf Krüger
Software developer | Nicolas Tröger
Software developer | Hans Killer
Software developer

## Product Goal
Product Vision | Project Mission
The Backup Cluster Manager software introduces a distributed approach into a system currently consisting of unconnected nodes . The software should demonstrate the benefits of a distributed approach, and should mirror real life use-cases and scenarios, and the effectiveness of using this approach. By using springboot, it can be easily integrated, and used as basis for enterprise projects while offering a user friendly UI built with Angular & TailwindCSS. | Creating an MVP for our industry partner which implements an alternative approach for managing distributed nodes. It offers an UI for editing and overview data from nodes as well as users and their permissions. The backend simulates backup nodes and how nodes will interact with each other. Frontend communicates with the backend to get/edit/delete data such as users, permissions as well as backups & cluster information.

## Product Glossary
Term | Definition
Cluster Manager | Supervisor instance that manages a set of SEP Sesam server nodes, handles registration of nodes, manipulation and synchronization of e.g. users, groups, and permissions or other meta data. Provides a REST interface for the Frontend and proxies requests to other nodes
SEP Sesam | SEP's Backup and Recovery software product, backups and restores are managed by a SEP Sesam Server
SEP Sesam Server Node, Node | Instance of SEP Sesam Server which shall be part of the cluster
Cluster Mode | Configuration flag on a node, indicating the node should join a cluster. In this mode, permissions and users shall be managed by the cluster manager
Supervisor Instance | Synonymous with Cluster Manager
Node Registration | Process of adding a node to a cluster
User / Group | Authenticated principals that can be created, modified and assigned permissions.
Client | A system that should be backed up by an SEP Sesam Server (e.g. a person's laptop computer)
Frontend, FE | The primary web UI, which runs in the browser and communicates with the CM's REST endpoints (directly, or via proxy, LB, etc TBD)
Synchronization Process | The mechanism of propagating information, such as users, groups, or permissions to downstream nodes
Proxy Functionality | The ability of issuing requests or listing data from a node via the CM's REST API
Backend, BE | Application / Code for the Cluster Manager and Simulated Server Node
Superuser | System user who has all permissions and can create new admins
Administrator | System users who can do and see everything except create/remove admins
Operator | System users who can see backups in the FE but not modify anything (read-only user)
Restore User | System users who can restore backups, no access to user management
Backup User | System users who can create backups, no access to user management

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Working MVP with FE, CM and 2 Nodes
5 | Working MVP with FE, CM and 2 Nodes
6 | Mid-Project Release
7 | Working Backup Schedules and Mock Tasks
8 | Working Permissions / User Groups + Bulk Data
9 | Advanced Cluster Management
10 | Advanced Cluster Management Pt2
11 | Groups/Permissions + Webflux
12 | Polishing + Metrics
13 | QA/Fixing
14 | Final Project Release

## Velocity Tracking
Sprint # | Story Points Realized | Story Points Committed | Average Story Points Realized
1 | 0 | 0 | 14.8333
2 | 13 | 15 | 14.8333
3 | 14 | 21 | 14.8333
4 | 20 | 21 | 14.8333
5 | 20 | 18 | 14.8333
6 | 20 | 18 | 14.8333
7 | 16 | 20 | 14.8333
8 | 4 | 7 | 14.8333
9 | 26 | 20 | 14.8333
10 | 15 | 13 | 14.8333
11 | 10 | 10 | 14.8333
12 | 20 | 17 | 14.8333
13 | 20 | 17 | 14.8333
14 |  | 12 | 14.8333
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity Chart
Sprint | Average Speed
2 | 13
3 | 13.5
4 | 15.6667
5 | 16.75
6 | 17.4
7 | 17.1667
8 | 15.2857
9 | 16.625
10 | 16.4444
11 | 15.8
12 | 16.1818
13 | 16.5
14 | 16.5
15 | 16.5

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 95 | 95
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | None |  | 2 | 95 | 0 | 95
2 | None |  | 15 | 93 | 13 | 95
3 | None |  | 21 | 78 | 14 | 82
4 | Working MVP with FE, CM and 2 Nodes |  | 21 | 57 | 20 | 68
5 | Working MVP with FE, CM and 2 Nodes |  | 18 | 36 | 20 | 48
6 | Mid-Project Release |  | 18 | 18 | 20 | 28
Features
1 | None
|  | Deciding our Tshirt design | 1 |  | 0
|  | Deciding our team logo | 1 |  | 0
2 | None
|  | Deciding our Tshirt design | 1 |  | 1
|  | Setup Build Process for Backend | 3 |  | 2
|  | Setup Basic Angular Project (Frontend) | 2 |  | 2
|  | Create first architecture draft | 3 |  | 3
|  | Setup Build Process For Frontend | 3 |  | 2
|  | Create Basic Spring Boot Project | 2 |  | 2
|  | Deciding our team logo | 1 |  | 1
3 | None
|  | Define entities for DBs | 3 |  | 3
|  | Create Docker Compose Configuration | 3 |  | 2
|  | Setup Database and Integrate it | 2 |  | 1
|  | Setup Dockerfile (Backend) | 3 |  | 2
|  | Create Basic UI Layout | 3 |  | 2
|  | Create Overview page | 3 |  | 3
|  | Add functionallity to sidebar | 1 |  | 1
|  | Create multiple pages for Router Outlet | 3 |  | 2
4 | Working MVP with FE, CM and 2 Nodes
|  | Backend: Create Cluster Manager | 3 |  | 3
|  | Frontend: Create Node Tab | 3 |  | 3
|  | Backend: Get Nodes API | 3 |  | 3
|  | Backend: Get Backups API | 3 |  | 3
|  | Frontend: Create Backups Tab | 3 |  | 3
|  | Frontend: Header moving while scrolling | 0 |  | 0
|  | Add Jacoco To Build And Integrate As Badge | 3 |  | 2
|  | Backend: Create User Node | 3 |  | 3
|  | Create Documentation | 0 |  | 0
|  | Create a test setup with 3 nodes | 0 |  | 0
|  | Backend: Create Database | 0 |  | 0
5 | Working MVP with FE, CM and 2 Nodes
|  | Create Documentation | 0 |  | 0
|  | Create a test setup with 3 nodes | 3 |  | 2
|  | Backend: Create Database | 3 |  | 1
|  | Backend: Add Pagination To APIs | 0 |  | 0
|  | Implement functions for DB | 3 |  | 5
|  | List Users | 0 |  | 0
|  | Create / Update / Delete User | 0 |  | 0
|  | Filter / Sort Backups | 0 |  | 0
|  | Bug: Main is not building | 2 |  | 2
|  | Backend: Implement node (un)registration process | 5 |  | 8
|  | Create Backup | 0 |  | 0
|  | Delete Backup | 0 |  | 0
|  | Filter / Sort Nodes | 0 |  | 0
|  | Create Build Process Video | 2 |  | 2
6 | Mid-Project Release
|  | Create Documentation | 0 |  | 0
|  | Create / Update / Delete User | 3 |  | 3
|  | Filter / Sort Nodes | 3 |  | 3
|  | Filter / Sort Backups | 0 |  | 0
|  | Create Backup | 5 |  | 5
|  | Delete Backup | 2 |  | 3
|  | Basic Backup Schedules | 0 |  | 0
|  | Mock Backup Tasks | 0 |  | 0
|  | Backend: Add Pagination To APIs | 3 |  | 3
|  | List Users | 2 |  | 3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Burn-down Chart (Mid-Project)
Burn-Down Chart
95 | 16.75
78.25 | 17.4
60.85 | 17.1667
43.6833 | 15.2857
28.3976 | 16.625
11.7726 | 16.4444
-4.6718 | 15.8

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 209 | 209
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | None |  | 0 | 209 | 0 | 209
2 | None |  | 15 | 209 | 13 | 209
3 | None |  | 21 | 194 | 14 | 196
4 | Working MVP with FE, CM and 2 Nodes |  | 21 | 173 | 20 | 182
5 | Working MVP with FE, CM and 2 Nodes |  | 18 | 152 | 20 | 162
6 | Mid-Project Release |  | 18 | 134 | 20 | 142
7 | Working Backup Schedules and Mock Tasks |  | 20 | 116 | 16 | 122
8 | Working Permissions / User Groups + Bulk Data |  | 7 | 96 | 4 | 106
9 | Advanced Cluster Management |  | 20 | 89 | 26 | 102
10 | Advanced Cluster Management Pt2 |  | 13 | 69 | 15 | 76
11 | Groups/Permissions + Webflux |  | 10 | 56 | 10 | 61
12 | Polishing + Metrics |  | 17 | 46 | 20 | 51
13 | QA/Fixing |  | 17 | 29 | 20 | 31
14 | Final Project Release |  | 12 | 12
Features
1 | None
|  | Deciding our Tshirt design | 0 |  | 0
|  | Deciding our team logo | 0 |  | 0
2 | None
|  | Deciding our Tshirt design | 1 |  | 1
|  | Setup Build Process for Backend | 3 |  | 2
|  | Setup Basic Angular Project (Frontend) | 2 |  | 2
|  | Create first architecture draft | 3 |  | 3
|  | Setup Build Process For Frontend | 3 |  | 2
|  | Create Basic Spring Boot Project | 2 |  | 2
|  | Deciding our team logo | 1 |  | 1
3 | None
|  | Define entities for DBs | 3 |  | 3
|  | Create Docker Compose Configuration | 3 |  | 2
|  | Setup Database and Integrate it | 2 |  | 1
|  | Setup Dockerfile (Backend) | 3 |  | 2
|  | Create Basic UI Layout | 3 |  | 2
|  | Create Overview page | 3 |  | 3
|  | Add functionallity to sidebar | 1 |  | 1
|  | Create multiple pages for Router Outlet | 3 |  | 2
4 | Working MVP with FE, CM and 2 Nodes
|  | Backend: Create Cluster Manager | 3 |  | 3
|  | Frontend: Create Node Tab | 3 |  | 3
|  | Backend: Get Nodes API | 3 |  | 3
|  | Backend: Get Backups API | 3 |  | 3
|  | Frontend: Create Backups Tab | 3 |  | 3
|  | Frontend: Header moving while scrolling | 0 |  | 0
|  | Add Jacoco To Build And Integrate As Badge | 3 |  | 2
|  | Backend: Create User Node | 3 |  | 3
|  | Create Documentation | 0 |  | 0
|  | Create a test setup with 3 nodes | 0 |  | 0
|  | Backend: Create Database | 0 |  | 0
5 | Working MVP with FE, CM and 2 Nodes
|  | Create Documentation | 0 |  | 0
|  | Create a test setup with 3 nodes | 3 |  | 2
|  | Backend: Create Database | 3 |  | 1
|  | Backend: Add Pagination To APIs | 0 |  | 0
|  | Implement functions for DB | 3 |  | 5
|  | List Users | 0 |  | 0
|  | Create / Update / Delete User | 0 |  | 0
|  | Filter / Sort Backups | 0 |  | 0
|  | Bug: Main is not building | 2 |  | 2
|  | Backend: Implement node (un)registration process | 5 |  | 8
|  | Create Backup | 0 |  | 0
|  | Delete Backup | 0 |  | 0
|  | Filter / Sort Nodes | 0 |  | 0
|  | Create Build Process Video | 2 |  | 2
6 | Mid-Project Release
|  | Create Documentation | 0 |  | 0
|  | Create / Update / Delete User | 3 |  | 3
|  | Filter / Sort Nodes | 3 |  | 3
|  | Filter / Sort Backups | 0 |  | 0
|  | Create Backup | 5 |  | 5
|  | Delete Backup | 2 |  | 3
|  | Basic Backup Schedules | 0 |  | 0
|  | Mock Backup Tasks | 0 |  | 0
|  | Backend: Add Pagination To APIs | 3 |  | 3
|  | List Users | 2 |  | 3
7 | Working Backup Schedules and Mock Tasks
|  | Basic Backup Schedules | 5 |  | 5
|  | Mock Backup Tasks | 5 |  | 3
|  | Create Documentation | 2 |  | 2
|  | Filter / Sort Backups | 3 |  | 1
|  | Authentication | 5 |  | 5
8 | Working Permissions / User Groups + Bulk Data
|  | Bug: Nodes Cannot Register (Auth) | 2 |  | 2
|  | Permission handling (Authorization) | 0 |  | 0
|  | Dynamic Page/Content Updates | 0 |  | 0
|  | Cluster Manager is a Node | 5 |  | 2
|  | Architecture Review / Revisit | 0 |  | 0
|  | Bulk Data Insertion / Preparation | 0 |  | 0
9 | Advanced Cluster Management
|  | Bulk Data Insertion / Preparation | 3 |  | 3
|  | Permission handling (Authorization) | 5 |  | 8
|  | Architecture Review / Revisit | 5 |  | 8
|  | Dynamic Page/Content Updates | 2 |  | 2
|  | Architecture Review: Proper Operation Foward | 5 |  | 5
10 | Advanced Cluster Management Pt2
| #146 | Updated Join Behavior | 5 |  | 5
| #147 | Managed/Unmanaged Mode | 5 |  | 5
| #148 | Shutdown, Restart and Remove | 3 |  | 5
11 | Groups/Permissions + Webflux
| #164 | Webflux Refresh | 0 |  | 0
| #165 | Update UI | 3 |  | 5
| #77 | Permissions/Groups Tab | 5 |  | 3
| #145 | Improve Data Caching | 0 |  | 0
| #173 | Tunneling Research | 2 |  | 2
| #183 | BUG: Not able to re-add node after shutdown | 0 |  | 0
| #184 | BUG: Shutdowned node should not be removed #184 | 0 |  | 0
| #185 | BUG: Automatic refresh doesn't work for nodes page | 0 |  | 0
12 | Polishing + Metrics
| #164 | Webflux Refresh | 5 |  | 8
| #145 | Improve Data Caching | 5 |  | 5
| #163 | Expose Metrics via Actuator/Prometheus | 5 |  | 3
| #194 | Stress Testing Research | 0 |  | 0
| #183 | BUG: Not able to re-add node after shutdown | 0 |  | 0
| #184 | BUG: Shutdowned node should not be removed #184 | 1 |  | 2
| #185 | BUG: Automatic refresh doesn't work for nodes page | 1 |  | 2
13 | QA/Fixing
| #194 | Stress Testing Research | 2 |  | 2
| #183 | BUG: Not able to re-add node after shutdown | 2 |  | 2
| #132 | Update Dashboard | 3 |  | 2
| #189 | Add Stress Testing Profiles | 0 |  | 0
| #200 | BUG: Backup Modal Window | 2 |  | 3
| #190 | Update UI #2 | 3 |  | 3
| #201 | Grafana Setup | 3 |  | 3
| #205 | Reactivate Backend testing | 2 |  | 5
14 | Final Project Release
| #189 | Add Stress Testing Profiles | 0 |  | 0
| #218 | Update Documentation | 3
| #215 | Update SBOM | 2
| #214 | Create Stress Testing Benchmarks & Documentation | 2
| #216 | Comment code | 2
| #217 | Reenable Frontend Test | 3

## Burn-down Chart (Final Release)
Burn-Down Chart
209 | 13
196 | 13.5
182.5 | 15.6667
166.8333 | 16.75
150.0833 | 17.4
132.6833 | 17.1667
115.5167 | 15.2857
100.231 | 16.625
83.606 | 16.4444
67.1615 | 15.8
51.3615 | 16.1818
35.1797 | 16.5
18.6797 | 16.5
2.1797 | 16.5

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
| Code review has been completed and code has been merged | Project builds, deploys, and tests successfully | Project can be opened on desktop browsers
| All feature branches have been merged and closed | Database update scripts succeed, consistency tests pass | Design documentation has been updated
| New feature code has been documented | Sprint release notes have been written | User documentation has been updated
| Component tests have been written and pass | Change log has been updated | The backend simulation must succeed and produce an artifact.
| Component builds with build pipeline | BOM is updated | The frontend should be able to handle user inputs & send them to the backend
Fulfills all acceptance criteria for item

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | Frontend | Tailwindcss | 4.1.16 | MIT License | Utility-first CSS Framework
2 | Frontend | Flowbite | 4.0.0 | MIT License | Component library built on Tailwind CSS.
3 | Frontend | Angular | 20.3.7 | MIT License | Web application framework
4 | Frontend | Angular Material | 20.2.13 | MIT | Material Design component library for Angular
5 | Frontend | typescript | 5.9.3 | Apache-2.0 | Superset of JavaScript
6 | Frontend | zonejs | 0.15.1 | MIT License | Execution context library for Angular
7 | Frontend | tslib | 2.8.1 | MIT License | Runtime library for TypeScript
8 | Frontend | karma | 6.4.4 | MIT License | Test runner
9 | Frontend | karma-chrome-launcher | 3.2.0 | MIT License | Launcher for Chrome browser in tests
10 | Frontend | karma-coverage | 2.2.1 | MIT License | Code coverage tool
11 | Frontend | karma-jasmine | 5.1.0 | MIT License | Adapter for Jasmine testing framework
12 | Frontend | karma-jasmine-html-reporter | 2.1.0 | MIT License | HTML reporter for test results
13 | Frontend | postcss | 8.5.6 | MIT License | Tool for transforming CSS with JavaScript
14 | Frontend | rxjs | 7.8.2 | Apache-2.0 | Library for reactive programming
15 | Frontend | Vite | 7.1.11 | MIT | Frontend build tool and bundler
16 | Frontend | Socket.io | 4.8.1 | MIT | Real-time bidirectional event-based communication
17 | Frontend | Algolia Search | 5.35.0 | MIT | Hosted search engine API client
18 | Frontend | Zod | 3.25.76 | MIT | TypeScript schema validation
19 | Frontend | Sass | 1.90.0 | MIT | CSS extension language
20 | Backend | postgresql(-docker) | latest | MIT | Relational database system
21 | Backend | PostgreSQL JDBC Driver | 42.7.7 | BSD-2 | Java Database Connectivity driver
22 | Backend | H2 | 2.3.232 | MLP 2.0 | In-memory database
23 | Backend | spring-boot | 3.5.6 | Apache-2.0 | Framework for creating production-grade Spring applications
24 | Backend | Flyway | 11.7.2 | Apache-2.0 | Database migration tool
25 | Backend | Spring WebFlux | 6.2.11 | Apache-2.0 | Reactive web framework
26 | Backend | Spring Data R2DBC | 3.5.4 | Apache-2.0 | Reactive relational database connectivity
27 | Backend | Spring Security | 6.5.5 | Apache-2.0 | Authentication and access control framework
28 | Backend | Spring Boot Actuator | 3.5.6 | Apache-2.0 | Production-ready features (metrics, health checks)
29 | Backend | Reactor Netty | 1.2.10 | Apache-2.0 | Asynchronous event-driven network application framework
30 | Backend | Reactor Core | 3.7.11 | Apache-2.0 | Reactive foundation for WebFlux
31 | Backend | HikariCP | 6.3.3 | Apache-2.0 | High-performance JDBC connection pool
32 | Backend | Apache Commons Lang | 3.18.0 | Apache-2.0 | Java utility library
33 | Backend | Apache Commons IO | 2.16.1 | Apache-2.0 | IO utility library
34 | Backend | SnakeYAML | 2.4 | Apache-2.0 | YAML parsing library
35 | Backend | Testcontainers | 1.21.3 | MIT | Java library for integration testing with Docker containers
36 | Backend | Micrometer | 1.15.4 | Apache-2.0 | Application metrics facade
37 | Backend | Lombok | 1.18.40 | MIT | Java library to reduce boilerplate code
38 | Backend | Logback | 1.5.19 | EPL-1.0/LGPL-2.1 | Default logging framework
39 | Backend | Jackson Databind | 2.19.2 | Apache-2.0 | JSON processor for REST APIs
40 | Backend | Hibernate Validator | 8.0.3.Final | Apache-2.0 | Bean validation provider (JSR 380)
41 | Backend | JUnit 5 | 5.12.2 | EPL-2.0 | Backend unit testing framework
42 | Backend | Mockito | 5.17.0 | MIT | Test mocking framework
43 | Backend | AssertJ | 3.27.4 | Apache-2.0 | Fluent assertions for testing
44 | Backend | Awaitility | 4.2.2 | Apache-2.0 | Testing for asynchronous systems
45 | Backend | Caffeine | 3.2.2 | Apache-2.0 | High-performance Java caching library
46 | Backend | Grafana | latest | AGPL-3.0 | Observability and data visualization platform
47 | Backend | k6 | latest | AGPL-3.0 | Open source load testing tool
48 | Backend | k6-reporter | latest | MIT | Open source tool for creating HTML test report

## Planning Poker
Last Name | First Name | Value
Wysokinska | Xemena |  | 2 | OK
Ostrizki | Jan
Raju | Robin Jose | 2
Nogu | Ervin | 2
Krüger | Landolf | 2 | 0 | No size
Tröger | Nicolas | 2 | 1 | Trivial size
#REF! | #REF! |  | 2 | Small size
Killer | Hans | 2 | 3 | Medium size
Schulze | Levin |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value